## Publication Plan
Pub Date | ORIG PUB DATE PLANNED | PROJECT | Action | Action Details | Docket # | Submit to OSG/FPT | Due Dates | Specific Project | 8260.43 | PTT | APWS | Docs sent to OSG | ATS Route Memo Signed | ATS Route Memo Sent to AJV-P | Sent to AJV-A | Environmental Review
2022-07-14 |  | VOR MON ZTL-1 | Amend 3 T-Routes Publish 9 T-Routes (new) | Amend T224(V20), T258(V66), T323(V97/267) Publish T404(V56/323), T406(V70), T410(V155), T412(V222W), T414(V222E), T423(V35), T425(V179), T427(V325S), T429(V325N) | 21-ASO-7 FR |  | 6/22/2021 Sent to OSG 7/13/2021 Due to AJV-P 9/26/2021 Due to FPT 10/26/2021 Due to AIS | ZTL (ATL/PDK/MCN/LDK) |  |  | NO
2022-07-14 |  | VOR MON ZTL-1 | Amend 1 T-Route Publish 1 T-Route (new) | Amend T215 Publish T408(V154) | 21-ASO-32 FR |  | 6/4/2021 Due to OSG 9/26/2021 Due to FPT | ZTL (ATL/PDK/MCN/LDK) |  |  | NO
2022-07-14 |  | VOR MON ZTL-1 | Amend 1 RNAV SID | Amend AGS JUNPR6 SID |  |  | 1/21/2022 Due to AIS 12/9/2021 Due to FPT | ZTL (ATL/PDK/MCN/LDK)
2022-07-14 |  | VOR MON ZTL-1 | Amend 2 CONV STARs | Amend STARs: CLT(CHPTR4, UNARM7) |  |  | 1/21/2022 Due to AIS 12/9/2021 Due to FPT | ZTL (ATL/PDK/MCN/LDK)
2022-07-14 |  | VOR MON ZTL-1 | Delete 4 CONV STARs | Delete: ATL(LGC5, RMG6, WHINZ4), PDK(DIFFI4) |  |  | 12/22/2021 Due to FPT 1/21/2022 Due to AIS | ZTL (ATL/PDK/MCN/LDK) |  |  | NO
2022-07-14 |  | VOR MON ZTL-1 | Amend 3 J-Routes Delete 1 J-Route | Amend J4(ATL), J45(ATL), J89(ATL) Delete J239(ATL) | 21-ASO-9 FR |  | 6/7/2021 Sent to OSG 11/21/2021 Due to FPT 12/21/2021 Due to AIS | ZTL (ATL/PDK/MCN/LDK) |  |  | NO
2022-07-14 |  | VOR MON ZTL-1 | Fix Action 1 (J52) | Amend FIBER fix to delete LDK from the -2 definition |  |  |  | ZTL (ATL/PDK/MCN/LDK) |  |  | NO
2022-07-14 |  | VOR MON ZTL-1 | Implement 2 Q-Routes | CANCEL THE ABOVE MENTIONED 5/19/2022 NA NOTAMs (Q139, Q184) |  |  |  | ZTL (ATL/PDK/MCN/LDK) |  |  | NO
2022-07-14 |  | VOR MON ZTL-1 | Delete 1 Victor Airways Amend 7 Victor Airways | Delete V362 (MCN) Amend V35 (MCN/ATL), V56 (MCN), V66 (MCN/ATL),V97 (MCN/ATL), V154 (MCN/ATL), V323 (MCN/ATL), V454 (MCN/ATL) | 21-ASO-8 FR |  | 11/21/2021 Due to FPT 12/21/2021 Due to AJV-A 6/22/2021 Sent to OSG | ZTL (ATL/PDK/MCN/LDK) |  |  | NO
2022-07-14 |  | VOR MON ZTL-1 | Amend 2 8260-2s (FPT) | Amend MOVIL(LDK/V209): FPT Fix action to redefine to remove LDK Amend DUBBS(GQO/V115): FPT Fix action to redefine to remove GQO (work with V115) |  |  | 12/21/2021 Due to AJV-A | ZTL (ATL/PDK/MCN/LDK) |  |  | NO
2022-07-14 |  | VOR MON ZTL-1 | Amend 5 Victor Airways | Amend V18 (LDK), V222 (ATL), V245 (LDK), V325 (ATL/MSL), V417 (ATL/LDK) | 21-ASO-14 FR |  | 11/21/2021 Due to FPT 12/21/2021 Due to AJV-A 6/22/2021 Sent to OSG | ZTL (ATL/PDK/MCN/LDK) |  |  | NO
2022-07-14 |  | VOR MON ZTL-1 | Amend 1 8260-2 (FPT) | Amend DIFFI(ATL): FPT Fix action to redefine to remove ATL REF: PDK RNAV(RNP) RWY 03R, PDK RNAV(RNP) Z RWY 21L |  |  | 12/21/2021 Due to AJV-A | ZTL (ATL/PDK/MCN/LDK) |  |  | NO
2022-07-14 |  | VOR MON ZME-1 | Amend 1 T-Route | Amend T251 (V9) | 21-ACE-11 FR |  | 9/21/2021 Sent to FPT 7/12/2021 Sent to AJV-P 6/10/2021 Sent to OSG | ZME(DYR/MAW/MON/MSL) - TEAM 3 |  |  | NO |  | signed
2022-07-14 |  | VOR MON ZME-1 | Amend 1 T-Route Publish 1 T-Routes (new) | Amend T354 (V47) Publish T421 (V7) | 21-ASO-10 FR |  | 9/21/2021 Sent to FPT 7/12/2021 Sent to AJV-P 6/10/2021 Sent to OSG | ZME(DYR/MAW/MON/MSL) - TEAM 3 |  |  | NO |  | signed
2022-07-14 |  | VOR MON ZME-1 | Delete 1 Victor Airway Amend 5 Victor Airways | Delete V397 (MON) Amend V47 (DYR), V54 (MSL), V140 (DYR/MAW), V278 (LDK/MON), V305 (MAW/MON) | 21-ASW-10 FR |  | 11/21/2021 Due to FPT 7/12/2021 Sent to AJV-P 6/21/2021 Sent to OSG | ZME(DYR/MAW/MON/MSL) - TEAM 3 |  |  | NO
2022-07-14 |  | VOR MON ZME-1 | Amend 1 Victor Airways | Amend V11 (DYR) | 21-ASO-13 FR |  | 11/21/2021 Due to FPT 7/12/2021 Sent to AJV-P 6/22/2021 Sent to OSG | ZME(DYR/MAW/MON/MSL) - TEAM 3 |  |  | NO
2022-07-14 |  | VOR MON ZME-1? | Amend 6 8260-2 (FPT) | Amend BANBI(CSG/V7/V521): FPT Fix action to redefine to remove CSG. Amend PETRY(TGE/V7/V521): FPT Fix action to redefine to remove TGE. Amend SHADY(TGE/V7/V521): FPT Fix action to redefine to remove TGE. Amend AVONS(MON/V94): FPT Fix action to redefine to remove MON. Amend HAMPT(MON/V278): FPT Fix action to redefine to remove MON & add TXK. Amend LOCUS(MON/V278/V305): FPT Fix action to redefine to remove MON & add TXK. |  |  |  | ZME(DYR/MAW/MON/MSL) - TEAM 3
2022-07-14 |  | VOR MON ZME-1 | Delete 1 STAR | Delete MEM STAR LUGOH3 |  |  | 12/22/2021 Due to FPT 1/21/2022 Sent to AJV-A | ZME(DYR/MAW/MON/MSL) - TEAM 3
2022-09-08 |  | VOR MON ZTL-1 | Amend 2 J-Routes Delete 4 J-Routes | Amend J22(PSK), J46(GQE/MEM/LIT), J48(ODF) Delete J39(GQO), J118(GQO/SPA/MEM), J145(ODF), J186(ODF) | 21-ASO-16 FR |  | 6/18/2021 Sent to OSG 11/21/2021 Due to FPT | ZTL (ATL/PDK/MCN/LDK) |  |  | NO
2022-09-08 |  | VOR MON ZTL-1 | Amend 1 J-Route Delete 1 J-Route Delete 1 Q-Route | Amend J20, J31, J41, J73 Delete J69 Delete Q63 | 21-ASO-15 FR |  | 6/21/2021 Sent to OSG 11/21/2021 Due to FPT | ZTL (ATL/PDK/MCN/LDK) not VOR MON work, but part of the overall ZTL high altitude redesign |  |  | NO
2022-09-08 |  | VOR MON ZME-1 | Amend 1 Victor Airway | Amend V175 (MAW) | 21-ACE-14 FR |  | 11/21/2021 Due to FPT 7/12/2021 Sent to AJV-P 6/21/2021 Sent to OSG | ZME(DYR/MAW/MON/MSL) - TEAM 3 |  |  | NO
2022-11-03 |  | VOR MON ZME-1 | Amend 2 T-Routes | Amend V7 (MSL), V9 (MAW) (moved from 21-ASO-13 to Team 1 docket) | 21-AEA-17 NPRM |  |  | ZME(DYR/MAW/MON/MSL) - TEAM 3
2022-09-08 | 2020-09-10 | NEC ACR | Amend 1 ATL SID (RNAV) | Amend ATL PLMMR3 SID (to coincide with Q22 and Q60) |  | 2/20/2020 (FPT) | 2/16/2022 Due to FPT | NEC ACR
2022-09-08 | 2020-09-10 | NEC ACR | Publish 9 Q-Routes (new) Amend 10 Q-Routes Amend 2 Q-Routes | Publish Q101, Q107, Q111, Q117, Q131, Q133, Q167, Q445, Q481 Amend Q22, Q60, Q85, Q87, Q97, Q99, Q109, Q113, Q135, Q409 Amend Q34, Q419 (post-implementation) | 21-AEA-11 NPRM | 10/5/2019 (OSG) 1/18/2020 (FPT) | 2/15/2022 Due to AJV-A 9/8/2021 Submitted to AJV-P 9/8/2021 Submitted to OSG | NEC ACR |  |  | NO
2022-09-08 |  | NEC ACR Post-Impl | Amend 1 Q-Route | Amend Q75 | 21-ASO-34 FR |  | 11/2/2021 Submitted to OSG 11/2/2021 Submitted to AJV-P | NEC ACR
2022-09-08 | 2020-09-10 | NEC ACR Offshore | Amend 4 Y-Routes Publish 1 Y-Route (new) | Amend Y299, Y309, Y319, Y323 Publish Y327 |  | 2/20/2020 (FPT) |  | NEC ACR Offshore |  |  | NO
2022-09-08 | 2020-09-10 | NEC ACR | Issue NA NOTAMs | NOTAM NA THE ABOVE Q-ROUTES/Y-ROUTES 9/8/2022-11-3/2022 (Except Q22, Q34, Q75, Q419, Y327) |  |  |  | NEC ACR |  |  | NO
2022-11-03 |  | NEC ACR Offshore | Amend 2 Y-Routes Publish 1 Y-Route (new) | Amend Y291, Y307 Publish Y313 |  |  |  | NEC ACR Offshore
2022-11-03 |  | NEC ACR Offshore | Amend 8 AR-Routes Delete 1 AR-Route | Amend AR15, AR16, AR17, AR18, AR19, AR22, AR23, AR24 Delete AR21 |  |  |  | NEC ACR Offshore
2022-11-03 | 2020-11-05 | NEC ACR | Implement Y-Routes/AR-Routes | CANCEL THE ABOVE MENTIONED 9/8/2022 Y-ROUTE NA NOTAMs |  |  |  | NEC ACR |  |  | NO
2022-11-03 | 2020-11-05 | NEC ACR | Delete 8 J-Routes Amend 4 J-Routes | Delete J37, J55, J79, J121 J165, J174, J191, J207, J209, J506, J561, J563, J573, J582, J585 Amend J14, J24, J52, J68 | 21-AEA-12 | 11/30/2019 (OSG) 3/14/2020 (FPT) | 11/3/2021 Due to OSG 12/28/2021 Due to AJV-P | NEC ACR |  |  | NO
2022-11-03 |  | NEC ACR | Delete 1 Q-Route Amend 1 Q-Route | Delete Q947 Amend Q81 (FL MP post-implementation) | 21-ASO-33 |  | 11/3/2021 Submitted to FPT 11/3/2021 Submitted to AJV-P | NEC ACR
2023-02-23 |  | NEC ACR Post-Impl | Publish 1 Q-Route (new) Amend 1 Q-Route | Publish Q141 (NOTAM NA) Amend Q437 | 22-AEA-5 |  |  | NEC ACR
2023-04-20 | 2020-11-05 | NEC ACR | Implement Q-Routes | CANCEL THE ABOVE MENTIONED 9/8/2022 Q-ROUTE NA NOTAMs
2023-04-20 | 2020-11-05 | NEC ACR | Delete 7 J-Routes (from 21-AEA-12) | Delete J37, J55, J79, J121, J174, J191, J209 | TBD | 11/30/2019 (OSG) 3/14/2020 (FPT) |  | NEC ACR |  |  | NO
2023-04-20 | 2020-11-05 | NEC ACR | Amend 4 PXT STARs (RNAV) | Amend STARs: PHL (JIIMS4, PAATS4), EWR (PHLBO4), TEB (JAIKE4) |  | 4/15/2020 (FPT) |  | NEC ACR |  |  | NO
2023-06-15 | 2020-12-31 | NEC ACR | Delete 1 EWR STAR (conv) | Delete EWR DYLIN4 STAR |  |  |  | NEC ACR
2023-06-15 |  | NEC ACR Post-Impl | Amend 1 Q-Route | Amend Q101 | TBD |  | 8/9/2022 Due to AJV-P
2022-12-29 |  | VOR MON ZTL-2 | Amend 1 CONV SID | Amend SIDs: CHA(CHA7) NOTE: MEM LUGOH4 STAR has GQO dependency (being worked by ZME VOR MON for 7/14/2022) |  |  |  | ZTL(CSG/HRS/GRD/GQO/TGE) |  |  | NO
2022-12-29 |  | VOR MON ZTL-2 | Amend 3 T-Routes Publish 5 T-Routes (new) Amend 2 T-Routes (Team1) | Amend T209 (V185), T239 (TGE), T292 Publish T424 (V16), T426 (V136), T437 (V37), T439 (V49), T441 (V53/185) Amend T255, T393 (Team 1) | 21-ASO-27 |  | 12/29/2021 Due to OSG | ZTL(CSG/HRS/GRD/GQO/TGE) |  |  | NO
2023-02-23 |  | VOR MON ZTL-2 | Amend 2 RNAV STARs | Amend STARs: CLT (BANKR3, JONZE3) |  |  |  | ZTL(CSG/HRS/GRD/GQO/TGE)
2023-02-23 |  | VOR MON ZTL-2 | Publish 1 RNAV STAR (new) Delete 2 CONV STARs | Publish CLT JOOLS STAR Delete STARs: CLT(CHPTR3, UNARM6) |  |  |  | ZTL(CSG/HRS/GRD/GQO/TGE)
2023-02-23 |  | VOR MON ZTL-2 | Amend 9 Victor Airways Delete 1 Victor Airway Amend 1 Victor Airway | Amend V16*, V37*, V53, V67, V136*, V159, V185, V209, V266* Delete V541 (non-VOR MON) Amend/redesign V379 (Team 1) | 21-ASO-26 |  | 2/23/2022 Due to OSG 4/19/2022 Due to AJV-P21 | ZTL(CSG/HRS/GRD/GQO/TGE) |  |  | NO
2023-02-23 |  | VOR MON ZTL-2 | Amend 4 8260-2 (FPT) | V168: Amend definition of CRAWL to remove CSG. V168: Amend definition of MILER to remove CSG and TGE. V168: Amend definition of KOMER to remove TGE. V168: Amend definition of CHIRP to remove TGE. FIX ACTIONS BANBI(CSG/V521), PETRY(TGE/V521), SHADY (V521/TGE) being handled under ZME-1 |  |  |  | ZTL(CSG/HRS/GRD/GQO/TGE) |  |  | NO
2023-10-05 |  | VOR MON ZJX | Amend 4 T-Routes Publish 3 T-Routes (new) Delete 1 T-Route | Amend T210(V198), T336(V521), T341(V157), T349(V7) Publish Tx35(V35), Tx579E(V579/V441), Tx579W(V579) Delete T204 | TBD |  |  | ZJX(AMG/CTY/GNV/TAY/VAN)
2023-10-05 |  | VOR MON ZJX | Amend 2 RNAV SIDs Publish 1 RNAV SID (new) | Amend SIDs: CHS(MLTRE3, SWPFX3) Publish JAX BRSTL1 SID |  |  |  | ZJX(AMG/CTY/GNV/TAY/VAN)
2023-10-05 |  | VOR MON ZJX | Delete 1 RNAV SID Delete 3 CONV STARs | Delete JAX ARNEY2 SID Delete JAX(AMG2), TPA(DARBS3, LZARD6) |  |  |  | ZJX(AMG/CTY/GNV/TAY/VAN)
2023-11-30 |  | VOR MON ZJX/ZMA | Amend 14 Victor Airways Delete 1 Victor Airway | Amend/Delete V3, V7, V35, V51, V97, V157, V198, V267, V295, V437, V441, V521, V537, V579 Delete V578 | TBD |  |  | ZJX/ZMA(AMG/CTY/GNV/TAY/VAN/CYY/LBV/PHK/TRV)
2023-11-30 |  | VOR MON ZMA | Amend/Delete 5 Victor Airways Delete 1 Victor Airway | Amend/Delete V159, V225, V492, V531, V601 Delete V529 | TBD |  |  | ZMA(CYY/LBV/PHK/TRV) - Team 2
2023-10-05 |  | VOR MON ZMA | Amend 1 Q-Route | Amend Q102 | TBD |  |  | ZMA(CYY/LBV/PHK/TRV) - Team 2
2023-10-05 |  | VOR MON ZMA | Amend 5 ATS Routes | Amend AR6*, AR15*, B9, BR62V, BR64V | TBD |  |  | ZMA(CYY/LBV/PHK/TRV) - Team 2
2024-01-27 |  | VOR MON ZMA | Amend 1 RNAV SID Amend 1 RNAV STAR | Amend RSW CSHEL6 SID Amend RSW SHFTY5 STAR |  |  |  | ZMA(CYY/LBV/PHK/TRV) - Team 2
2024-01-27 |  | VOR MON ZMA | Amend/Delete 10 CONV STARs Amend/Delete 8 CONV SIDs | Amend/Delete STARs: FLL(BLUFI4, DVALL3, FORTL9), MCO(MINEE5, GOOFY7), MIA(ANNEY4), PBI(STOOP3), TPA(BRDGE8), RSW(JOSFF5), APF(ZEILR5) Amend/Delete SIDs: APF(APF5), MLB(MLB7), RSW(SCUBY7), PBI(PBI2), PIE(PIE9), SRQ (SRQ5), TPA(LGTNG3, TAMPA7) |  |  |  | ZMA(CYY/LBV/PHK/TRV) - Team 2
TBD |  | VOR MON ZMA | Fix Actions | V533(OVIDO/TRV), V539(MILES/LBV), V581(DADES/GNV), V599/V511(THNDR/LBV) | TBD
2023-04-20 |  |  | Removed from 21-ASO-8 | Amend V5 (MCN/ATL), V20 (MCN/ATL), V155 (MCN/ATL) | TBD
2023-04-20 |  |  | Removed from 21-ASO-14 | Amend V241 (ATL), V321 (ATL) | TBD
2023-06-15 |  |  | Removed from 21-ASO-8 | Delete V243 (MCN/ATL) Amend V51 (MCN/ATL), V267 (MCN/ATL) | TBD
2023-06-15 |  |  | Removed from 21-ASO-14 | Delete V311 (ATL), V415 (ATL), V463 (ATL) Amend V115 (LDK), V333 (ATL) | TBD
2023-08-10 |  |  | Removed from 21-ASO-8 | Delete V179 (MCN/ATL), V578 (MCN) Amend V70 (MCN) | TBD
2027-04-15 |  |  | Removed from 21-ASW-10 | Amend V69 (MAW/MON), V94 (MON) | TBD
TBD |  | PBN BOS MASSPORT BLK 2 | Amend 8 BOS SIDs Amend 3 BOS STARs | Amend BOS RNAV SIDs (BLZZR6, BRUWN7, CELTK7, HYLND7, LBSTA8, PATSS7, REVSS6, SSOXS7) Amend BOS RNAV STARs (JFUND3, OSHN6, ROBUC4) |  |  |  | BOS MASSPORT BLOCK 2 |  |  | NO
TBD |  | VOR MON ZTL-3 | Amend/Delete 6 Victor Airways | Delete/Amend V1, V136, V139, V155, V259, V296 | TBD
TBD |  | VOR MON ZTL-3 | These include FLO but no other ZJX/ZMA VORs | Amend JQF KABEE3 RNAV STAR Amend/Delete X CONV STARs: CLT(RASLN3), AGS(STWRT3) Amend/Delete X CONV SIDs: CLT(KNI2, CLT2), FAY(MTY4), HKY(HKY3)
TBD |  | PBN ATL | Amend ATL SIDs | (to clear waivers, SLICC)
TBD |  | ZBW-NAVCANADA | Amend 2 Q-Routes Publish 1 T-Route (new to U.S.) NavCanada Only (3 Routes) | Amend Q951 (to POSTS..PADDE..SVM..GADAV [CSA/ZOB], KATEK..DAVDA..SSENA..TALNO [CSA/ZOB], and KERVA..DANOL [ESA/ZBW]) Amend Q907 (to TBD) Publish T739 (to KATEK..DAVDA..SSENA..TALNO and KERVO..MLT..DANOL) NavCanada to Delete T791, Amend T721, Q929 (No U.S./FAA Action Required) | TBD
TBD |  | PBN PWM | Amend 2 PWM STARs | Amend PWM STARs (CDOGG5, SCOGS4) |  |  | TBD Due to FPT | Date Tentative |  |  | NO
TBD | 2020-11-05 | TEAM 1 | Publish 1 PXT STAR (RNAV new) | Publish LGA PROUD1 STAR | TBD
TBD | 2020-12-31 | TEAM 1 | Delete 1 LGA STAR (conv) | Delete LGA KORRY4 STAR |  | 6/10/2020 (FPT) |  |  |  |  | NO
PUBLISHED/IMPLEMENTED/COMPLETED ACTIONS
2022-05-19 |  | VOR MON ZTL-1 | Amend 5 RNAV SIDs | Amend SIDs: ATL(VRSTY3, WIGLE3, BANNG3, HAALO3, SMLTZ3) |  |  | PUBLISHED | ZTL (ATL/PDK/MCN/LDK) |  |  | NO
2022-05-19 |  | VOR MON ZTL-1 | Amend 5 Q-Routes Publish 1 Q-Route (new) | Amend Q19(J45/ATL/J73), Q30(J52/LDK/ZME), Q79(ATL), Q89(ATL), Q118(ATL) Publish Q184(ATL/J4/20) | 21-ASO-6 FR |  | PUBLISHED | ZTL (ATL/PDK/MCN/LDK) |  |  | NO |  | signed
2022-05-19 |  | VOR MON ZTL-1 | Amend 5 Q-Routes Publish 1 Q-Route (new) | Amend Q65, Q77, Q93, Q103(PSK), Q116(MEM) Publish Q139(GQO) | 21-ASO-11 FR |  | PUBLISHED | ZTL (ATL/PDK/MCN/LDK) part of the overall ZTL high altitude redesign |  |  | NO
2022-05-19 |  | VOR MON ZME-1 | Amend 1 SID (CSA AOR) | Amend STL CHUUC6 SID (RNAV) |  |  | PUBLISHED
2022-05-19 |  | VOR MON ZME-1 | Publish 3 T-Routes (new) | Publish T370 (V278), T398 (V54), T419 (V305/V47) | 21-ASW-7 FR |  | PUBLISHED | ZME(DYR/MAW/MON/MSL) - TEAM 3 |  |  | NO
2022-05-19 |  | VOR MON ZME-1 | Amend 1 SID (CSA AOR) | Amend STL CHUUC6 SID (RNAV) |  |  | PUBLISHED
2022-05-19 |  | VOR MON ZME-1 | Publish 3 T-Routes (new) | Publish T370 (V278), T398 (V54), T419 (V305/V47) | 21-ASW-7 FR |  | PUBLISHED | ZME(DYR/MAW/MON/MSL) - TEAM 3 |  |  | NO
2022-05-10 | 2020-10-08 | NEC ACR | Establish ZDC Ultra-Hi Sector 30 | Establish ZDC Ultra-High Sector 30 (Carolina Beach High) |  |  | IMPLEMENTED |  |  |  | NO
2022-03-24 |  | PBN BOS MASSPORT-2 | Amend 1 BOS IAP | Amend BOS RNAV (RNP) X RWY33L |  |  | PUBLISHED | BOS MASSPORT BLOCK 1 |  |  | NO
2022-03-24 |  | VOR MON ZTL-3 | Amend 2 8260-2 (FPT) | Amend PERRI(PSK)/J8 and OAKLE(PSK)/J24: FPT Fix action to redefine to remove VOR |  |  | COMPLETED | ZTL (ATL/PDK/MCN/LDK) |  |  | NO
2022-03-24 |  | VOR MON ZME-1 | Amend 1 STAR | Amend MEM RNAV STAR WLDER1 |  |  | PUBLISHED | ZME(DYR/MAW/MON/MSL) - TEAM 3 |  |  | NO
2022-03-24 |  | VOR MON ZME-1 | Amend 1 STAR | Amend MEM RNAV STAR WLDER1 |  |  | PUBLISHED | ZME(DYR/MAW/MON/MSL) - TEAM 3 |  |  | NO
2021-12-02 | 2020-11-05 | NEC ACR | Implement 4 Q-Routes | CANCEL THE ABOVE MENTIONED 10/7/2021 NA NOTAMs (Q419, Q22, Q437, Q34) |  |  | IMPLEMENTED
2021-12-02 | 2020-11-05 | NEC ACR | Delete 4 J-Route Amend 2 J-Routes | Delete J150, J193, J222, J225 Amend J42 (DELETE TXK-BOS), J191 (DELETE HPW-RBV ONLY) | 20-ASO-31 FR | 11/30/2019 (OSG) 3/14/2020 (FPT) | PUBLISHED
2021-12-02 | PBN CHS | Amend 1 CHS STAR | Amend CHS BAGGY3 STAR |  |  |  | PUBLISHED | NO
2021-12-02 |  | PBN BOS MASSPORT-1 | Amend 8 BOS SIDs | Amend BOS RNAV SIDs (BLZZR5, BRUWN6, CELTK6, HYLND6, LBSTA7, PATSS6, REVSS5, SSOXS6) |  |  | PUBLISHED | BOS MASSPORT BLOCK 1 |  |  | NO
2021-10-07 |  | NEC ACR Post | Amend 1 WRI STAR | Amend WRI WAALK2 STAR |  |  | PUBLISHED |  |  |  | NO
2021-10-07 | 2020-09-10 | NEC ACR | Publish 1 Q-Routes (new) Amend 1 Q-Route Amend 2 Q-Routes | Publish Q419, NOTAM NA (ALL/BROSS./.DPK) Amend Q22, NOTAM NA (BEARI./.FOXWD) Amend Q54, Q64 NOTAM NA (TYI./.SAWED) UNTIL 11/3/2022 | 20-AEA-22 FR | 10/5/2019 (OSG) 1/18/2020 (FPT) | PUBLISHED |  |  |  | NO
2021-10-07 | 2020-09-10 | NEC ACR | Publish 1 Q-Route (new) | Publish Q437, NOTAM NA (ALL/VILLS./.SLANG) | 20-AEA-19 FR |  | PUBLISHED |  |  |  | NO
2021-10-07 | 2020-09-10 | NEC ACR | Amend 1 Q-Route | Amend Q34, NOTAM NA (SWAPP./.RBV) | 20-ASO-28 FR |  | PUBLISHED |  |  |  | NO
2021-10-07 | 2020-09-10 | NEC ACR | Amend 1 Q-Route | Amend Q29 | 20-ASO-30 FR |  | PUBLISHED |  |  |  | NO
2021-10-07 | 2020-09-10 | NEC ACR | Issue NA NOTAMs | NOTAM NA Q22, Q34, Q419, Q437 as noted above 10/7/2021-12/2/2021 |  |  | ISSUED |  |  |  | NO
2021-10-07 | 2020-09-10 | NEC ACR | Issue NA NOTAM | NOTAM NA Q64 (TYI./.SAWED) 10/7/2021-11/3/2022 |  |  | ISSUED
2021-10-07 | 2020-09-10 | NEC ACR | Amend 1 ATL SID (RNAV) | Amend ATL PHIIL3 SID |  | 2/20/2020 (FPT) | PUBLISHED |  |  |  | NO
2021-10-07 |  | NEC ACR Offshore | Amend 5 Y-Routes Amend 2 AR-Routes Delete 2 AR-Routes | Amend Y289, Y299, Y307, Y438, Y494 (Changes to Y307, Y438, Y494 to be implemented 10/7) Amend AR3, AR5 (Changes to be implemented 10/7) Delete AR7, AR25 (Changes to be implemented 10/7) |  |  | PUBLISHED |  |  |  | NO
2021-10-07 |  | NEC ACR Offshore | Amend 4 Y-Routes Amend 7 AR-Routes | Amend Y291, Y309, Y323, Y436 (Changes to Y436 to be implemented 10/7) Amend AR12, AR15, AR16, AR17, AR18, AR21, AR23 (Changes to be implemented 10/7) |  |  | PUBLISHED |  |  |  | NO
2021-10-07 | 2020-09-10 | NEC ACR | Issue NA NOTAMs (reissue) | NOTAM NA Y291, Y309, Y319(reissue same), Y323 10/7/2021-9/8/2022 |  |  | ISSUED
2021-10-07 | 2020-09-10 | NEC ACR | Issue NA NOTAMs (reissue) | NOTAM NA Y289, Y299 10/7/2021-11/3/2022 |  |  | ISSUED |  |  |  | NO
2021-10-07 | 2020-09-10 | NEC ACR | Issue NA NOTAMs (reissue) | NOTAM NA Q85, Q87, Q97, Q109, Q113, Q135, Q409 10/7/2021-9/8/2022 |  |  | ISSUED
2021-10-07 |  | VOR MON ZBW-11 | Amend 1 MHT SID | Amend MHT PPORT4 RNAV SID |  |  | PUBLISHED | Group 11 (EEN/HUL/LEB/LWM/MSS/PSM/SLK/UCA) |  |  | NO | Group 11 (HUL/LEB/LWM/MSS/SLK)
2021-10-07 |  | VOR MON ZBW-11 | Amend 2 Victor Airways | Amend V39, V93 | 21-AEA-6 FR |  | PUBLISHED | Group 11 (EEN/HUL/LEB/LWM/MSS/PSM/SLK/UCA) |  |  | NO
2021-10-07 |  | VOR MON ZBW-11 | Amend 1 BOS SID | Amend BOS WYLYY4 RNAV SID (Block 1) |  |  | PUBLISHED | Group 11 (EEN/HUL/LEB/LWM/MSS/PSM/SLK/UCA) |  |  | NO
2021-10-07 |  | VOR MON ZJX - FL MP | Delete 1 CONV SID Delete 3 RNAV STARs | Delete MCO JAG6 SID Delete STARs: MCO(COSTR3, BAIRN4), TPA(DEAKK5) |  |  | DELETED
2021-10-07 |  | VOR MON ZMA - FL MP | Delete 1 CONV SID Delete 3 CONV STARs Delete 5 RNAV STARs Delete 1 RNAV SID | Delete MIA POTTR7 SID Delete STARs: MIA(CYY1), FLL(GISSH5), PBI(TUXXI3) Delete STARs: MIA(HILEY7, SSCOT5), FLL(FISEL7), PBI (FRWAY5), BCT(CAYSL4) Delete PBI BUFIT2 SID |  |  | DELETED
2021-10-07 |  | PBN CHS | Delete 1 CHS SID Publish 1 CHS SID | Delete CHS PLFMD2 SID Publish CHS STUNO1 SID |  |  | PUBLISHED |  |  |  | NO
2021-08-12 |  | NEC ACR Post | Amend 1 DOV STAR | Amend DOV ARLFT2 STAR |  |  | Published |  |  |  | NO
2021-08-12 |  | VOR MON ZBW-11 | Amend 4 8260-2s (FPT) | FPT Fix actions to redefine to remove dependent VORs; Fixes will not be removed from the routes: SEEDY(PSM)/V139 [Flight Inspection Reqd] SILVE(PSM)/V139 ARMIE(PSM)/V167 CEKAY(PSM)/V167, V268 |  |  | COMPLETED
2021-08-12 |  | VOR MON ZTL-1 | Amend 1 CONV SID | Amend TYS KNOXVILLE7 SID |  |  | Published | ZTL (ATL/PDK/MCN/LDK) |  |  | NO
2021-06-17 |  | VOR MON ZBW-11 | Publish 6 T-Routes (new) Amend 5 T-Routes Publish 1 Q-Route (new) Amend 2 Q-Routes Amend 9 Victor Airways Delete 10 Victor Airways | Publish T314, T315, T316, T634, T662, T698 Amend T295, T391, T608, T705, T781 Publish Q864 Amend Q806, Q844 Amend V2, V3, V14, V29, V106, V229, V249, V273, V471 Delete V145, V196, V203, V282, V318, V322, V352, V428, V490, V542 | 20-AEA-10 FR |  | PUBLISHED | Group 11 (EEN/HUL/LEB/LWM/MSS/PSM/SLK/UCA) |  |  | NO
2021-06-17 |  | VOR MON ZBW-11 | Amend 1 PWM STAR | Amend PWM CDOGG4 RNAV STAR |  |  | PUBLISHED | Group 11 (EEN/HUL/LEB/LWM/MSS/PSM/SLK/UCA) |  |  | NO
2021-06-17 | 2021-06-17 | VOR MON ZBW-11 | Amend 4 8260-2s (FPT) | FPT Fix actions to redefine to remove dependent VORs; Fixes will not be removed from the routes: PRENT(HUL)/V300 completed TEBOR(UCA)/V433 completed KERST(LEB)/V447 completed RUCKY(LEB)/V447 completed |  | 2021-06-23 | PUBLISHED | Group 11 (EEN/HUL/LEB/LWM/MSS/PSM/SLK/UCA) |  |  | NO
2021-06-17 |  | VOR MON ZTL-1 | Amend 1 CONV STAR | Amend ATL SINCA7 STAR |  |  | Published | ZTL (ATL/PDK/MCN/LDK) |  |  | NO
2021-04-22 |  | VOR MON ZTL-1 | Amend 2 CONV SIDs | Amend SIDs: ATL (ATL1), BHM (BHM8) |  |  | Submtd to AJV-A | ZTL (ATL/PDK/MCN/LDK) |  |  | NO
2021-04-22 |  | VOR MON ZTL-1 | Amend 1 CONV SID Amend 6 CONV STARs | Amend BNA NASHVILLE8 SID Amend STARs: ATL(LGC6, RMG7, WHINZ5), CLT(CHPTR3, UNARM7), PDK(DIFFI5) |  |  | Completed
2021-02-25 | 2020-11-05 | NEC ACR | Amend 7 RDU SIDs (RNAV) Amend 4 RDU STARs (RNAV/conv) Delete 3 RDU STARs (RNAV/conv) Publish 1 RDU STAR (RNAV new) Delete 3 RDU SIDs (conv) Amend 2 RDU SIDs (conv) | Amend RDU SIDs: (BEXGO4, HOOKZ4, HURIC4, LWOOD4, OXFRD4, ROZBO4, SHPRD4) Amend RDU STARs: (ALDAN3 RNAV, BLOGS3 RNAV, BUZZY9 [conv], MALNR5 RNAV) Delete RDU STARs (KAROO2 RNAV, ARGAL6 [conv], SOUTH BOSTON6 [conv]) Publish RDU TAQLE1 STAR Delete RDU SIDs (TAR HEEL1, FAYETTVILLE4, BLUE DEVIL6) Amend RDU SIDs: (RALEIGH1, PACKK9) |  | 4/15/2020 (FPT) | PUBLISHED
2021-02-25 |  | VOR MON ZBW Group 11 (EEN/HUL/LEB/LWM/MSS/PSM/SLK/UCA) | Amend 2 Victor Airways Delete 2 Victor Airways | Amend V141, V542 Delete V151, V496 | 19-AEA-8 FR |  | PUBLISHED
2021-02-25 |  | VOR MON ZBW Group 11 (EEN/HUL/LEB/LWM/MSS/PSM/SLK/UCA) | Amend 2 BED RNAV (RNP) IAPs | Amend BED RNAV (RNP) IAPs ( Y RWY 11, Y RWY 29) |  |  | PUBLISHED
2020-11-05 | No CHANGE | NEC ACR | Implement 8 Q-Routes | CANCEL THE ABOVE MENTIONED 9/10/2020 NA NOTAMs (8 Q/Y-ROUTES) |  |  | IMPLEMENTED
2020-11-05 | No CHANGE | NEC ACR | Amend 1 PXT STAR (RNAV) Publish 4 PXT STARs (RNAV new) Delete 4 PXT STARs (conv) Amend 3 CHS SIDs (RNAV) Amend 2 CHS STARs (RNAV) Amend 4 CHS IAPs | Amend TEB MAZIE3 STAR Publish STARs: LGA (APPLE1), EWR (BRAND1), DOV (ARLFT1), WRI (WAALK1) Delete STARs: LGA (GATBY1), EWR (RUUTH1), DOV (SMYRNA3), WRI (SEA ISLE4) Amend CHS SIDs (PLMTO3, LGRHD3, JZI-KIAWAH2) Amend CHS STARs: (AMYLU3, OSPRI7) Amend CHS RNAV (GPS) Y APCHs (RWYS 03, 21, 15, 33) |  | 4/15/2020 (FPT) | PUBLISHED
2020-11-05 | No CHANGE | NEC ACR | Delete 5 J-Routes/Q-Route Amend 3 J-Routes Amend 3 J-Routes change docket | Delete J109, J230, J62, J570, Q108 Amend (per original 19-ASO-27) J2 (TAY-DEFUN), J39 (CEW-MGM), J61 (EDDYS-EMI) Amend (with changes) J37 (ALB-MSS), J55 (CHS-TUBAS), J121 (BRIGS-ENE) | 19-ASO-27 FR | 11/30/2019 (OSG) 3/14/2020 (FPT) | PUBLISHED
2020-09-10 | No CHANGE | NEC ACR | Publish 7 Q-Routes (new) Amend 1 Q-Routes | Publish Q119, Q127, Q129, Q220, Q430, Q439, Q450 Amend Q480 | 18-AEA-16 FR | 10/5/2019 (OSG) 1/18/2020 (FPT) | PUBLISHED
2020-09-10 | No CHANGE | NEC ACR | Issue NA NOTAMs | NOTAM NA ALL OF THE ABOVE Q-ROUTES (EXCEPT Q480) 9/10/2020-11/5/2020 |  |  | PUBLISHED
2020-07-16 | No CHANGE | NEC ACR | Amend 10 J-Routes Delete 8 J-Routes | Amend J14, J20, J41, J43, J45, J52, J73, J85, J89, J91 Delete J40, J51, J53, J75, J81, J97, J210, J575 | 19-ASO-18 FR | 8/10/2019 (OSG) 11/24/2019 (FPT) | PUBLISHED
2020-05-21 | No CHANGE | NEC ACR | Amend 2 Q-Routes | Amend Q75, Q475 | 19-AEA-9 FR |  | PUBLISHED
2020-05-21 | No CHANGE | NEC ACR | Amend 1 DOV SID | Amend DOV CANNY1 SID |  |  | PUBLISHED
2020-03-26 | No CHANGE | NEC ACR | Amend 6 DC METS SIDs (RNAV) | Amend SIDs: BWI (FIXET3, TERPZ7), IAD/DCA (SCRAM5, JDUBB3), HEF (GABBE3), ADW (JEFSN1) |  |  | PUBLISHED
2020-01-30 | No CHANGE | NEC ACR | Delete 5 CHS STARs (RNAV) | Delete CHS STARs (DDENA1, GMSTR1, MKNZI1, RSRVE1, TRTLS4) |  |  | PUBLISHED
2019-11-07 | No CHANGE | NEC ACR | Implement ZDC Low Alt. Changes | Reorganize ZDC Low Altitude Sectors - Combine 3 Sectors (24, 25, 28) into Sector 25 EWN Low |  |  | IMPLEMENTED
2019-10-10 | No CHANGE | NEC ACR | Publish 1 Y-Route (new) | Publish Y578 with NEC NY Offshore |  |  | PUBLISHED
2019-10-10 | No CHANGE | NEC ACR | Publish/Amend 3 Waypoints Add 5 Published Holding Patterns | Publish Stand-Alone Waypoints LOVRR, RANAY, Amend Location of Waypoint ORCHA Add Published Holding Patterns at BZNGA, FUUFF, MAYKR, PUNGO, TANJA |  |  | PUBLISHED

## Timelines
ENTER CHART DATE -> |  | 2022-11-03 | NEC ACR Publication/Rulemaking Timelines | [6 empty] | Part 95 | Part 71 19-AEA-9 | Part 95 | Part 71 19-ASO-18 | Part 95 | Part 71 18-AEA-16 | Part 95 | Part 71 19-ASO-27 | Part 95 | Part 95 | Part 95 | Part 95 | Part 95 | Part 95 | Part 95 | Part 95
Process Days | Owner | Date | Merged Process Playbook | Rulemaking Process (Part 71 Procedures) [310 days] | Publication Process (Part 71 Routes)[205 days] | Publication Process (Part 95 Procedures)[174 days] | Preferred IFR Routes, CDRs, Playbooks, NASR Frequencies | Process Days | Owner | 2020-03-26 | 2020-05-21 | 2020-05-21 | 2020-07-16 | 2020-07-16 | 2020-09-10 | 2020-09-10 | 2020-11-05 | 2020-11-05 | 2020-12-31 | 2021-02-25 | 2021-04-22 | 2021-06-17 | 2021-08-12 | 2021-10-07 | 2021-12-02
365 | CWG | 2021-11-03 | Submit draft ATS Route Memo to OSG (D-340) | Submit draft ATS Route Memo to OSG (D-340) |  |  |  | 340 | NEC ACR |  | 2019-06-16 |  | 2019-08-11 |  | 2019-10-06 |  | 2019-12-01 | 2019-12-01 | 2020-01-26 | 2020-03-22 | 2020-05-17 | 2020-07-12 | 2020-09-06 | 2020-11-01 | 2020-12-27
310 | OSG | 2021-12-28 | Submit ATS Route Memo to AJV-P21 (D-310) | Submit ATS Route Memo to AJV-P21 (D-310) |  |  |  | 310 | OSG |  | 2019-07-16 |  | 2019-09-10 |  | 2019-11-05 |  | 2019-12-31 | 2019-12-31 | 2020-02-25 | 2020-04-21 | 2020-06-16 | 2020-08-11 | 2020-10-06 | 2020-12-01 | 2021-01-26
305 | AJV-P21 | 2022-01-02 | Submit draft NPRM to AGC (D-305) | Submit draft NPRM to AGC (D-305) |  |  |  | 305 | AJV-P21 |  | 2019-07-21 |  | 2019-09-15 |  | 2019-11-10 |  | 2020-01-05 | 2020-01-05 | 2020-03-01 | 2020-04-26 | 2020-06-21 | 2020-08-16 | 2020-10-11 | 2020-12-06 | 2021-01-31
275 | AGC | 2022-02-01 | Provide comments/edits to AJV-P21 (D-275) | Provide comments/edits to AJV-P21 (D-275) |  |  |  | 275 | AGC |  | 2019-08-20 |  | 2019-10-15 |  | 2019-12-10 |  | 2020-02-04 | 2020-02-04 | 2020-03-31 | 2020-05-26 | 2020-07-21 | 2020-09-15 | 2020-11-10 | 2021-01-05 | 2021-03-02
270 | AJV-P21 | 2022-02-06 | Submit final/edited/AJV-11-signed NPRM to AGC (D-270) | Submit final/edited/AJV-11-signed NPRM to AGC (D-270) |  |  |  | 270 | AJV-P21 |  | 2019-08-25 |  | 2019-10-20 |  | 2019-12-15 |  | 2020-02-09 | 2020-02-09 | 2020-04-05 | 2020-05-31 | 2020-07-26 | 2020-09-20 | 2020-11-15 | 2021-01-10 | 2021-03-07
260 | AGC | 2022-02-16 | Publish in Federal Register (D-260) | Publish in Federal Register (D-260) |  |  |  | 260 | AGC |  | 2019-09-04 |  | *2/4/2020* |  | *3/24/2020* |  | *3/23/2020* | *3/23/2020* | *3/23/2020* | *3/23/2020* | *3/23/2020* | *3/23/2020* | *3/23/2020* | *3/23/2020* | *3/23/2020*
235 | CWG | 2022-03-13 | Submit Route Documentation to FPT (D-235) |  | Submit Route Documentation to FPT (D-235) |  |  | 235 | NEC ACR |  | 2019-09-29 |  | 2019-11-24 |  | 2020-01-19 |  | 2020-03-15 | 2020-03-15 | 2020-05-10 | 2020-07-05 | 2020-08-30 | 2020-10-25 | 2020-12-20 | 2021-02-14 | 2021-04-11
215 | AGC | 2022-04-02 | 45-day comment period ends (D-215) | 45-day comment period ends (D-215) |  |  |  | 215 | AGC |  | 2019-10-19 |  | *3/20/2020* |  | *5/8/2020* |  | *5/7/2020* | *5/7/2020* | *5/7/2020* | *5/7/2020* | *5/7/2020* | *5/7/2020* | *5/7/2020* | *5/7/2020* | *5/7/2020*
205 | FPT | 2022-04-12 | Submit Route Documentation to AIS (D-205) |  | Submit Route Documentation to AIS (D-205) |  |  | 205 | OSG/FPT |  | 2019-10-29 |  | 2019-12-24 |  | 2020-02-18 |  | 2020-04-14 | 2020-04-14 | 2020-06-09 | 2020-08-04 | 2020-09-29 | 2020-11-24 | 2021-01-19 | 2021-03-16 | 2021-05-11
204 | CWG | 2022-04-13 | Submit Procedure Documentation to FPT (D-204) |  |  | Submit Procedure Documentation to FPT (D-204) |  | 205 | NEC ACR | 2019-09-03 |  | 2019-10-29 |  | 2019-12-24 |  | 2020-02-18 |  | 2020-04-14 | 2020-06-09 | 2020-08-04 | 2020-09-29 | 2020-11-24 | 2021-01-19 | 2021-03-16 | 2021-05-11
174 | FPT | 2022-05-13 | Submit Procedure Documentation to AIS (D-174) |  |  | Submit Procedure Documentation to AIS (D-174) |  | 175 | OSG/FPT | 2019-10-03 |  | 2019-11-28 |  | 2020-01-23 |  | 2020-03-19 |  | 2020-05-14 | 2020-07-09 | 2020-09-03 | 2020-10-29 | 2020-12-24 | 2021-02-18 | 2021-04-15 | 2021-06-10
140 | AIS | 2022-06-16 | Rule-Making/Part 71 Enroute to Flight Inspection (D-140) |  | Rule-Making/Part 71 Enroute to Flight Inspection (D-140)
125 | OSG | 2022-07-01 | Submit responses and effective date to AJV-11 (D-125) | Submit responses and effective date to AJV-11 (D-125) |  |  |  | 125 | OSG |  | 2020-01-17 |  | 2020-03-13 |  | 2020-05-08 |  | 2020-07-03
120 | AJV-P21 | 2022-07-06 | Submit final rule to AGC for legal sufficiency (D-120) | Submit final rule to AGC for legal sufficiency (D-120) |  |  |  | 120 | AJV-P21 |  | 2020-01-22 |  | 2020-03-18 |  | 2020-05-13 |  | 2020-07-08
107 | CWG | 2022-07-19 | Submit North Atlantic Route (NAR) Amendments to ATCSCC |  |  |  | Submit North Atlantic Route (NAR) Amendments to ATCSCC
108 | AIS | 2022-07-18 | Enroute to Flight Inspection (NON-Rule-Making) (D-108) |  |  | Enroute to Flight Inspection (NON-Rule-Making) (D-108)
90 | AGC | 2022-08-05 | Complete final rule (D-90) | Complete final rule (D-90) |  |  |  | 90 | AGC |  | 2020-02-21 |  | 2020-04-17 |  | 2020-06-12 |  | 2020-08-07
90 | NFDC | 2022-08-05 | Notify AJV-11 that Flight Inpection Complete/Sat (D-90) | Notify AJV-11 that Flight Inpection Complete/Sat (D-90) |  |  |  | 90 | NFDC |  | 2020-02-21 |  | 2020-04-17 |  | 2020-06-12 |  | 2020-08-07
88 | AIS | 2022-08-07 | NON-Enroute to Flight Inspection (NON-Rule-Making) |  |  | NON-Enroute to Flight Inspection (NON-Rule-Making)
77 | CWG | 2022-08-18 | Submit Preferred IFR Route Amendments to ATCSCC |  |  |  | Submit Preferred IFR Route Amendments to ATCSCC | 70 | NEC ACR | 2020-01-16 | 2020-03-12 | 2020-03-12 | 2020-05-07 | 2020-05-07 | 2020-07-02 | 2020-07-02 | 2020-08-27 | 2020-08-27 | 2020-10-22 | 2020-12-17 | 2021-02-11 | 2021-04-08 | 2021-06-03 | 2021-07-29 | 2021-09-23
68 | AJV-P21 | 2022-08-27 | Submit final rule with AJV-11 signature to AGC (D-68) | Submit final rule with AJV-11 signature to AGC (D-68) |  |  |  | 68 | AJV-P21 |  | 2020-03-14 |  | 2020-05-09 |  | 2020-07-04 |  | 2020-08-29 | 2020-08-29 | 2020-10-24 | 2020-12-19 | 2021-02-13 | 2021-04-10 | 2021-06-05 | 2021-07-31 | 2021-09-25
60 | ATCSCC | 2022-09-04 | Submit Preferred IFR Route Amendments to NFDC |  |  |  | Submit Preferred IFR Route Amendments to NFDC | 60 | ATCSCC | 2020-01-26 | 2020-03-22 | 2020-03-22 | 2020-05-17 | 2020-05-17 | 2020-07-12 | 2020-07-12 | 2020-09-06 | 2020-09-06 | 2020-11-01 | 2020-12-27 | 2021-02-21 | 2021-04-18 | 2021-06-13 | 2021-08-08 | 2021-10-03
58 | AGC | 2022-09-06 | Publish final rule in Federal Register (D-58) | Publish final rule in Federal Register (D-58) |  |  |  | 58 | AGC |  | 2020-03-24 |  | *4/28/2020* |  | 2020-07-14 |  | 2020-08-29: 2020-09-08
63 | CWG | 2022-09-01 | Submit Playbook and CDR Amendments to ATCSCC |  |  |  | Submit Playbook and CDR Amendments to ATCSCC
49 | AIT/NFDC | 2022-09-15 | NASR Subcriber Files Available from NFDC FOR REVIEW |  | NASR Subcriber Files Available from NFDC FOR REVIEW | NASR Subcriber Files Available from NFDC FOR REVIEW |  | 49 | NFDC |  | 2020-04-02 |  | 2020-05-28 | 2020-05-28 | 2020-07-23 | 2020-07-23 | 2020-09-17 | 2020-09-17 | 2020-11-12 | 2021-01-07 | 2021-03-04 | 2021-04-29 | 2021-06-24 | 2021-08-19 | 2021-10-14
56 | ATCSCC | 2022-09-08 | Forward CDR Amendments to ARTCCs |  |  |  | Forward CDR Amendments to ARTCCs
40 | CWG | 2022-09-24 | Submit Frequency Assignment for NASR udpates to NFDC |  |  |  | Submit Frequency Assignment for NASR udpates to NFDC
36 | ARTCC | 2022-09-28 | Last day to update CDRs in RMT |  |  |  | Last day to update CDRs in RMT
35 | CWG | 2022-09-29 | Last day to pull back procedures (NASR Daemon Date) |  | Last day to pull back procedures (NASR Daemon Date) | Last day to pull back procedures (NASR Daemon Date) |  | 35 | NEC ACR | 2020-02-20 | 2020-04-16 | 2020-04-16 | 2020-06-11 | 2020-06-11 | 2020-08-06 | 2020-08-06 | 2020-10-01 | 2020-10-01 | 2020-11-26 | 2021-01-21 | 2021-03-18 | 2021-05-13 | 2021-07-08 | 2021-09-02 | 2021-10-28
28 | AIT/NFDC | 2022-10-06 | NASR Subcriber Files Available to the Public |  | NASR Subcriber Files Available to the Public | NASR Subcriber Files Available to the Public |  | 28 | NFDC | 2020-02-27 | 2020-04-23 |  | 2020-06-18 |  | 2020-08-13 | 2020-08-13 | 2020-10-08 | 2020-10-08 | 2020-12-03 | 2021-01-28 | 2021-03-25 | 2021-05-20 | 2021-07-15 | 2021-09-09 | 2021-11-04
19 | AIT/NFDC | 2022-10-15 | Terminal Procedures Charts Available |  | Terminal Procedures Charts Available | Terminal Procedures Charts Available |  | 19 | ADT | 2020-03-07 |  | 2020-05-02 |  | 2020-06-27 |  | 2020-08-22 |  | 2020-10-17 | 2020-12-12 | 2021-02-06 | 2021-04-03 | 2021-05-29 | 2021-07-24 | 2021-09-18 | 2021-11-13
19 | AIT/NFDC | 2022-10-15 | High/Low Altitude Enroute Charts Available |  | High/Low Altitude Enroute Charts Available | High/Low Altitude Enroute Charts Available |  | 19 | ADT |  | 2020-05-02 |  | 2020-06-27 |  | 2020-08-22 |  | 2020-10-17
0 | AIT/NFDC | 2022-11-03 | New ATS Route(s)/Procedure(s) Effective/Published |  | New ATS Route(s)/Procedure(s) Effective/Published | New ATS Route(s)/Procedure(s) Effective/Published |  | 0 | NFDC | 2020-03-26 | 2020-05-21 | 2020-05-21 | 2020-07-16 | 2020-07-16 | 2020-09-10 | 2020-09-10 | 2020-11-05 | 2020-11-05 | 2020-12-31 | 2021-02-25 | 2021-04-22 | 2021-06-17 | 2021-08-12 | 2021-10-07 | 2021-12-02
Dates in blue font are actuals i.e. *4/28/2020*
http://aerochart.faa.gov/index.asp?xml=enroute/chartlist_controller

## Pub Slot Requirements
TEAM | 2022-01-27 | 2022-03-24 | 2022-05-19 | 2022-07-14 | 2022-09-08 | 2022-11-07 | 2022-12-29 | 2023-02-23 | 2023-04-20 | 2023-06-15 | 2023-08-10 | 2023-10-05 | 2023-11-30 | 2024-01-25 | 2024-03-21 | 2024-05-16
Team 1 VOR MON
Team 2 NEC ACR |  |  |  |  | 18 | 33 | 2
Team 2 VOR MON |  |  | 40 | 44 |  |  | 9 | 17 | 36 | 5 | 11
Team 2 MASSPORT |  | 1 |  | 11
Team 3 VOR MON |  |  | 9 | 12
Florida Metroplex |  |  | 30
Other
IAPs
Total | 0 | 1 | 79 | 67 | 18 | 33 | 11 | 17 | 36 | 5 | 11 | 0 | 0 | 0 | 0 | 0 | 278 | TOTAL
DELETIONS
TEAM | 2022-01-27 | 2022-03-24 | 2022-05-19 | 2022-07-14 | 2022-09-08 | 2022-11-07 | 2022-12-29 | 2023-02-23 | 2023-04-20 | 2023-06-15 | 2023-08-10 | 2023-10-05 | 2023-11-30 | 2024-01-25 | 2024-03-21 | 2024-05-16
Team 1 VOR MON
Team 2 NEC ACR
Team 2 VOR MON
Team 2 MASSPORT
Team 3 VOR MON
Florida Metroplex
Other
IAPs
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TOTAL
75

## Change Log
Date | Change(s)
2021-05-01 | Moved 18 Q-Routes to 9/8/2022: Publish Q101, Q107, Q111, Q117, Q131, Q133, Q167, Q445, Q481 Amend Q60, Q85, Q87, Q97, Q99, Q109, Q113, Q135, Q409
2021-05-01 | Moved 19 Jet Routes to 11/7/2022: Delete J37, J55 (DELETE REMAINDER OF ROUTE TUBAS-HUBBS), J79, J121, J165, J174, J191 (DELETE REMAINDER OF ROUTE HPW-ILM), J207, J209, J506, J561, J563, J573, J582, J585 Amend J14, J24, J52, J68 NOTE: J55 and J191 above will be amend on 12/2/2021 and completely deleted on 11/3/2022
2021-05-01 | Moved 4 Y-Routes to 9/8/2022: Amend Y291, Y309, Y319, Y323 NOTE: Y291, Y309, Y323 will be amended on 10/7/2021 and again on 9/8/2022
2021-05-01 | Moved 9 AR-Routes to 11/3/2022: Amend AR15, AR16, AR17, AR18, AR19, AR21, AR22, AR23, AR24 NOTE: AR15, AR16, AR17, AR18, AR21, AR23 will be amended on 12/2/2021 and again on 11/3/2022.
2021-05-01 | Moved 5 STARs to 11/3/2022: Amend STARs: PHL (JIIMS4, PAATS4), EWR (PHLBO4), TEB (JAIKE4) Publish LGA PROUD1 STAR
2021-05-01 | Moved 2 STARs to 12/29/2022 Delete STARs: LGA (KORRY4), EWR (DYLIN4)
2021-05-15 | Added 1 CONV SID and 6 CONV STARs for 5/19/2022: Amend BNA NASHVILLE8 SID Amend STARs: ATL(LGC6, RMG7, WHINZ5), CLT(CHPTR3, UNARM7), PDK(DIFFI5)
2021-06-14 | Added 5 RNAV STARs for 5/19/2022: ATL (WIGLE3, BANNG3, HAALO3, SMLTZ3) and AGS (JUNPR6)
2021-06-14 | Moved T215 to separate docket (21-AGL-1), still to publish on 5/19/2022.
2021-06-14 | Moved BOS WYLYY4 RNAV SID (Block 1) to 10/7/2021.
2021-06-14 | Moved V39 and V93 to 10/7/2021.
2021-06-14 | Added 2 fix actions for 1/27/2022: Amend PERRI(PSK)/J8 and OAKLE(PSK)/J24 to delete PSK from the -2 definition
2021-06-14 | Added 1 fix action for 7/14/2022: Amend FIBER fix to delete LDK from the -2 definition
2021-06-14 | Added 2 STARs (ZTL Group 2) for 12/29/2022: Amend STARs: CLT (BANKR3, JONZE3)
2021-06-14 | Added 1 SID (ZTL Group 2) for 12/29/2022: Amend SID: CHA(CHA7) Amend MEM LUGOH4 STAR (being worked by ZME VOR MON for 5/19/2022 for MSL)
2021-06-14 | Added 5 T-Routes (ZTL Group 2) for 1/29/2022: Amend T209(V185), T239(TGE) Publish Tx49(V49), Tx53/185(V53/185) Amend T292 (non-VOR MON) NOTE: Additional T-Routes will likely be needed (estimated number: 5-8)
2021-06-14 | Added 12 Victor Airways (ZTL Group 2) for 2/23/2023: Amend V16, V37, V53, V67, V136, V159, V168, V185, V266, V521 Delete V209 Delete V541 (non-VOR MON)
2021-06-14 | Added 2 Q-Routes (SPA RELO) for 7/22/2024: Amend Q22, Q60
2021-06-14 | Added Q63 for 7/11/2024 (ZID request following Q93 amended Delete Q63)
2021-06-15 | Removed T365 NEW from the project (no longer needed).
2021-06-15 | Amend STARs: CLT (BANKR3, JONZE3) DATE CHANGE FROM 12/29/22 TO 9/8/22
2021-06-17 | Moved 4 8260-2s fix actions to 8/12/2021: SEEDY(PSM)/V139 [Flight Inspection Reqd] SILVE(PSM)/V139 ARMIE(PSM)/V167 CEKAY(PSM)/V167, V268
2021-06-21 | Moved the AGS JUNPR6 SID to its own row, still for 5/19/2022 (for now)
2021-06-22 | Moved 2 SIDs to 10/7/2021 Delete CHS PLFMD2 SID Publish CHS STUNO1 SID
2021-06-22 | Moved Amend WRI WAALK2 STAR to 10/7/2021
2021-06-22 | Moved Q63 Deletion to 7/14/2022 with docket 21-ASO-15.
2021-06-22 | V243 and V578 in this docket were changed from being an amendment to being a total deletion.
2021-06-23 | Removed T402 from the project (5/19/2022)
2021-06-23 | Added multiple rows for ZJX and ZMA VOR MON for 4/20/2023, 6/15/2023, and 8/10/2023
2021-06-28 | Updated docket for T215 to 21-AGL-27 for 5/19/2022 (from 21-AGL-1 same date).
2021-06-30 | Added V245 (LDK) to docket# 21-ASO-14 for 7/14/2022.
2021-06-30 | Added for 7/14/2022: Amend MOVIL(LDK): FPT Fix action to redefine to remove LDK.
2021-07-01 | Added placeholders for 4 T-Routes for ZTL-2
2021-07-01 | Moved from 6/15/2023 to 4/20/2023: Amend AR6, AR15, B9, BR62V, BR64V
2021-07-09 | Moved 5 ATL SIDs from 5/19/2022 to 3/24/2022 (coordination pending with ZTL) Amend SIDs: ATL(VRSTY3, WIGLE3, BANNG3, HAALO3, SMLTZ3) Leaving Amend AGS JUNPR6 SID for 5/19/2022 most likely (coordination pending with ZTL) | corrected to show 5 SIDs (vs 4)
2021-07-09 | Moved Q22 from 2024 to 9/8/2022, the amendment for 10/7/2021 will remain for NEC ACR Deleted Q60 from 2024, incorporating with amendment planned for 9/8/2022 for NEC ACR
2021-07-09 | Clarification: J55 and J191 will be amended in phases, both on 12/2/2021 and 11/3/2022
2021-07-09 | Changed NASHVILLE8 to completed 4/22/2021
2021-07-09 | Moved 2 STARs to their own row, but left 5/19/2022 date pending coordination with ZTL on date change to 3/24/2022 Amend STARs: CLT(CHPTR3, UNARM7)
2021-07-09 | Fix action unchanged pending confirmation with FPT: Perhaps the DIFFI STAR amendment with mitigate the ATL dependency: Amend DIFFI(ATL): FPT Fix action to redefine to remove ATL
2021-07-09 | Moved 2 CLT STARs to 12/29/2022 with other STARs for ZTL-2
2021-07-09 | Change LUGOH STAR for 12/29/2022 to a NOTE to track dependency on GQO
2021-07-09 | Completed addition of CONV SIDs and STARs for ZMA VOR MON for 8/10/2023.
2021-07-13 | Added V521 to V deletions under ZJX for 6/15/2023 (left on ZTL-2 as well, but may be fix actions only BANBI/PETRY/SHADY).
2021-07-13 | ZME-1 Added fix actions for BANBI/PETRY/SHADY for 7/14/2022 for V7 and V521 (OZR request to retain V7.) ZME-1 Added fix actions for AVONS(V94), LOCUS(V278/V305), HAMPT(V278) for 7/14/2022.
2021-07-13 | ZTL-1 Added fix action to Amend DUBBS(GQO/V115): FPT Fix action to redefine to remove GQO (work with V115 below). I'm not sure this is needed but wanted to capture the mitigation of GQO.
2021-07-13 | Added ATL PLMMR SID for 9/8/2022 to coincide with Q20 and Q60 (replace SPA with BURGG)
2021-07-14 | Added for 10/7/2021: NOTAM NA Q64 10/7/2021-11/3/2022 (TYI./.SAWED)
2021-07-15 | Added V35 to ZJX/ZMA for 6/15/2023. Added V155 to ZJX for 6/15/2023 (BLOTS).
2021-07-19 | Amendments for 5/19/2022 changed to deletions: Delete: ATL(LGC6, RMG7, WHINZ5), PDK(DIFFI5)
2021-07-21 | Changes placeholder T-Routes for 12/29/2022 to "Publish T-Routes Tx16, Tx37"
2021-07-22 | Added for 2/23/2023: Publish CLT GIFFT1 STAR Delete STARs: CLT(CHPTR3, UNARM6)
2021-07-22 | Added new Tx136(V136) for 12/29/2022
2021-07-22 | REMINDER to add to docket 21-AEA-12 deletion of VUZ./.SQS.
2021-07-22 | Moved to 2/23/2023 from 12/29/2022: Amend STARs: CLT (BANKR3, JONZE3)
2021-07-26 | Move 2 STARs to 7/14/2022 from 5/19/2022: Amend STARs: CLT(CHPTR3, UNARM7)
2021-07-26 | Move 4 STARs to 7/14/2022 from 5/19/2022: Delete: ATL(LGC6, RMG7, WHINZ5), PDK(DIFFI5)
2021-07-26 | Move 1 SID to 7/14/2022 from 5/19/2022: Amend AGS JUNPR6 SID
2021-07-26 | Delete J55 from 12/2/2021 (consolidate changes on 11/3/2022)
2021-07-27 | Added for 3/21/2024: Delete Q947
2021-07-30 | Added CLT2 for 4/20/2023
2021-08-01 | MOOKY6 deleted from 8/10/2023
2021-08-02 | Moved MHT PPORT STAR to 10/7/2021 (from 8/12/2021)
2021-08-10 | Moved to 3/24/2022: Fix actions OAKLE and PERRI
2021-08-16 | added fix actions for 2/23/2022: Fix actions for V168 V168: Amend definition of CRAWL to remove CSG. V168: Amend definition of MILER to remove CSG and TGE. V168: Amend definition of KOMER to remove TGE. V168: Amend definition of CHIRP to remove TGE. V521: Amend BANBI to remove CSG. V521: Amend PETRY to remove TGE. V521:Amend SHADY to remove TGE.
2021-08-16 | V209 changed to segment deletion (was route deletion) for 2/23/2023
2021-08-16 | V168 and V521 removed from rulemaking list on 2/23/2023, changed to fix actions only: route to be retained.
2021-08-16 | V185 changed from segment deletion to route deletion on 2/23/2023.
2021-08-16 | ZDC airspace changes postponed from 9/9/2021 to TBD
2021-08-16 | V175 moved from 7/14/2022 to 9/8/2022.
2021-08-16 | Moved from 5/19/2022 to 3/24/2022: Amend STL CHUUC6 SID (RNAV) Amend MEM RNAV STAR WLDER1
2021-08-16 | Moved from 5/19/2022 to 7/14/2022: Amend MEM RNAV STARs LUGOH4
2021-08-16 | Moved from 1/27/2022 to TBD: Amend PWM STARs (CDOGG5, SCOGS4)
2021-08-16 | Moved from 7/14/2022 to TBD: Amend BOS RNAV SIDs (BLZZR6, BRUWN7, CELTK7, HYLND7, LBSTA8, PATSS7, REVSS6, SSOXS7) Amend BOS RNAV STARs (JFUND3, OSHN6, ROBUC4)
2021-09-13 | Added V136 to ZJX from ZMA for 6/15/2023 (planning purposes only)
2021-09-14 | Moved V492 and V531 from ZJX to ZMA for 6/15/2023 (planning purposes only)
2021-09-20 | Changed ZDC airspace changes to 11/4/2021
2021-09-20 | Add Q34 and Q419 to docket 21-AEA-11 for 9/8/2022 (need to add to APWS). Need to change the legal for Q22 to reflect ZDC/ZNY requested changes.
2021-09-20 | Added cancellation of Q947 for 3/21/2024 under ZBW (need to add to APWS, could these be accommodated on 9/8/2022/21AEA-11 or 11/7/2022/21-AEA-12?).
2021-09-22 | Added note for potential fix actions for V1, AR6, and AR15
2021-10-04 | Added amendment of Q81 for 11/3/2022 under NEC ACR (for FL Metroplex)
2021-11-01 | Added the ZBW/NavCanada proposal for Q951, Q907, T739 to row with Q947. Changed date to TBD.
2021-11-03 | Added amendment of Q75 for 11/3/2022 under NEC ACR Post-Implementation 21-ASO-34.
2021-11-03 | Updated hyperlinks to NPRM for ZME-1 VOR MON dockets 12-ACE-11, 21-ASW-7, and 21-ASO-10.
2021-11-04 | LUGOH STAR moved to 9/8/2022 and changed to a deletion.
2021-11-04 | J-Route deletions/amendments for 21-ASO-16 and 21-ASO-15 moved from 7/14/2022 to 9/8/2022.
2021-11-26 | 21-AGL-27 changed to 21-AOS-32 for T215 with publication date TBD.
2021-12-02 | 12/2/2021 publications complete, NOTAMs cancelled.
2021-12-03 | 21-ASO-32 moved from 5/19/2022 to 7/14/2022 (T215).
2021-12-03 | T408 moved from 21-ASO-7 to 21-ASO-32 for 7/14/2022 publication.
2021-12-08 | Amend SIDs: ATL(VRSTY3, WIGLE3, BANNG3, HAALO3, SMLTZ3) moved from 3/24/2022 to 5/19/2022
2022-01-12 | Tentatively identified Q139 and Q184 to NOTAM N/A from 5/19/2022-7/14/2022.
2022-01-13 | Removed multiple routes from 21-ASO-8, 21-ASO-14 to "just in time" future chart dates with docket# TBD:
2022-01-13 | Removed multiple routes from 21-ASO-13 and 21-ASW-10 to "just in time" future chart dates with docket# TBD:
2022-01-21 | Updated docket 21-ASO-8 for 7/14/2022 to reflect changes to amendments/deletions: V154 no longer a complete deletion, will be amending to delete a segment. V323 no longer a complete deletion, will be amending to delete a segment. V35 changed to delete fewer segments. V56 changed to delete fewer segments. V66 changed to delete fewer segments. V97 changed to delete fewer segments. V454 changed to delete fewer segments.
2022-01-21 | Updated docket 21-ASO-14 for 7/14/2022 to reflect changes to amendments/deletions: V325 no longer a complete deletion, will be deleting a segment. V417 no longer a complete deletion, will be deleting a segment. V18 changed to delete fewer segments. V222 changed to delete fewer segments. V245 no change.
2022-01-21 | Updated docket 21-ASW-10 for 7/14/2022 to reflect changes to amendments/deletions: V397 no change. V47 no change. V54 no change. V140 changed to delete fewer segments. V278 changed to delete fewer segments. V305 changed to delete fewer segments.
2022-01-28 | 21-ASO-7 NPRM moved from 5/19/2022 to 7/14/2022: T323 and T414 went to Flight Inspection but unsure if they will publish on 5/19 or will be kept with the other routes in the dockdet.
2022-01-31 | Correct T408 in docket 21-ASO-32 to a new publication (vs. and amendment).
2022-02-08 | Added Amend T255, T393 to 21-ASO-27 for 12/29/2022 for ESA PBN Team 1.
2022-02-14 | Changes the entries for the amendments to the CLT CHPTR3 and UNARM6 to show CHPTR4 and UNARM7.
2022-02-15 | Changes the entries for the amendments to Delete: ATL(LGC5, RMG6, WHINZ4), PDK(DIFFI4) to reflect the correct numbers.
2022-02-15 | Changes the entries for the amendments to Delete: MEM LUGOH3 to reflect the correct number.
2022-02-21 | Added Team 1 docket number 21-AEA-17 to V-7 and V-9 for publication on 9/8/2022 (moved from 21-ASO-13).
2022-03-10 | Amendments to Y291, Y309, Y319, Y323 for 9/8/2022 publication have been changed (to be re-submitted). See the Change Tracker.
2022-03-10 | Amend AR16, AR18, AR19, AR22, AR24 for 11/3/2022 publication have been changed (to be re-submitted). AR21 was changed to total route deletion (to be re-submitted as a route deletion). See the Change Tracker.
2022-03-10 | Amendments to AR15, AR17, AR23 are unchanged from the original submission for 11/3/2022 publication.
3/10//2022 | Two new Y-Routes (T313, Y327) and two Y-Route amendments (Y299, Y307) were added for 11/3/2022 publication.
2022-03-10 | New Q-Route Q141 added for NEC ACR Post implementation for 4/20/2023, 22-AEA-5
2022-03-21 | Added Q437 for amendment for NEC ACR Post implementation for 4/20/2023, 22-AEA-5
2022-03-22 | Plan to NOTAM NA Q139 and Q184 removed/stikethrough.
2022-03-23 | Q141 and Q437 (22-AEA-5) moved to 2/23/2023.
2022-03-23 | 21-ASO-10 (T354,T421) moved to 7/14/2022.
2022-03-23 | Confirmed 21-ASO-7 and 21-ASO-32 (ZTL VOR MON T-Routes for 7/14/2022 publication.
2022-04-01 | Added Amend Q101 (post-implementation) for 4/20/2023, docket number TBD.
2022-05-04 | Y291, Y307,Y313 to publish on 11/3/2022.
2022-05-04 | Y299, Y309, Y319, Y323, Y327 to publish on 9/8/2022. All to be NOTAM'd NA EXCEPT Y327 (amend JAINS./.DIW prefs to JAINS Y327 SKARP WETRO : leave JAINS./.ILM as is)
2022-05-16 | Moved new PROUD1 and KORRY4 deletion to TBD and Team 1
2022-06-01 | Q101 amendment for 4/23/2023 removed (subsequently added back, see change log entry on 6/20/2022).
2022-06-13 | ZJX and ZMA plan revised following recent FWG meetings.
2022-06-13 | 21-AEA-17 moved to 11/3/2022 (V7, V9, and other Team 1 routes) V7 to delete MSL-VUZ only, V9 to delete MAW-GQE only.
2022-06-13 | V185 in docket 21-ASO-26 changed from a deletion to an amendment (deleting SOT to IRQ only).
2022-06-13 | Amend/redesign V379 (Team 1) moved to Team 2 docket 21-ASO-26.
2022-06-21 | Removed amendments to J20, J41, and J73 Docket 21-ASO-15 for publication 9/8/2022.
2022-06-22 | Changed the 9/8/20222 NEC ACR NA NOTAMs to include Y327 per ZDC request.
2022-06-27 | Q101 amendment add for 6/15/2023 (extend from TUGGR to KALDA).
2022-06-28 | The amendment to J46 was removed from the final rule for 21-ASO-6 for publication 9/8/2022.
2022-06-29 | Moved to 4/20/2023 Delete J37, J55, J79, J121, J174, J191, J209 (from 11/3/2022, Docket 21-AEA-12)
2022-06-29 | Moved to 4/20/2023 Amend STARs: PHL (JIIMS4, PAATS4), EWR (PHLBO4), TEB (JAIKE4) (from 11/3/2022)
2022-06-29 | Moved to 6/15/2023 Delete EWR DYLIN4 STAR (from 12/29/2022)

## Airway Lists
COUNTS | 161 |  |  |  | 38 |  | 18 |  | 72 |  | 20 |  | 24 | 14 | 347
| NEC ACR | PUB | running tally | % complete | ZBW-11 | PUB | ZME | PUB | ZTL1 | PUB | ZTL2 | PUB | ZJX | ZMA
| Y578 | 2019-10-10 | 1 | 0.6211% | T314 | 2020-06-17 | T370 | 2022-05-19 | Q19 | 2022-05-19 | T209 | 2022-12-29 | T204 | V225 | x
| J4 | 2020-01-30 | 2 | 1.242% | T315 | 2020-06-17 | T398 | 2022-05-19 | Q30 | 2022-05-20 | T239 | 2022-12-29 | V1 | V492 | x
| J20 | 2020-01-30 | 3 | 1.863% | T316 | 2020-06-17 | T419 | 2022-05-19 | Q79 | 2022-05-21 | T292 | 2022-12-29 | V56 | V511 | x
| J37 | 2020-01-30 | 4 | 2.484% | T634 | 2020-06-17 | T251 | 2022-07-14 | Q89 | 2022-05-22 | T424 | 2022-12-29 | V136 | V529 | x
| J41 | 2020-01-30 | 5 | 3.106% | T662 | 2020-06-17 | T354 | 2022-07-14 | Q118 | 2022-05-23 | T437 | 2022-12-29 | V139 | V531 | x
| J43 | 2020-01-30 | 6 | 3.727% | T698 | 2020-06-17 | T421 | 2022-07-14 | Q184 | 2022-05-24 | T439 | 2022-12-29 | V155 | V539 | x
| J45 | 2020-01-30 | 7 | 4.348% | T295 | 2020-06-17 | V397 | 2022-07-14 | Q65 | 2022-05-25 | T441 | 2022-12-29 | V159 | V599 | x
| J46 | 2020-01-30 | 8 | 4.969% | T391 | 2020-06-17 | V47 | 2022-07-14 | Q77 | 2022-05-26 | T426 | 2022-12-29 | V198 | V601 | x
| J51 | 2020-01-30 | 9 | 5.59% | T608 | 2020-06-17 | V54 | 2022-07-14 | Q93 | 2022-05-27 | V16 | 2023-02-23 | V259 | Q102 | deleted
| J52 | 2020-01-30 | 10 | 6.211% | T705 | 2020-06-17 | V140 | 2022-07-14 | Q103 | 2022-05-28 | V37 | 2023-02-23 | V581 | AR6 | x
| J53 | 2020-01-30 | 11 | 6.832% | T781 | 2020-06-17 | V278 | 2022-07-14 | Q116 | 2022-05-29 | V53 | 2023-02-23 | V3 | AR15 | x
| J55 | 2020-01-30 | 12 | 7.453% | Q864 | 2020-06-17 | V305 | 2022-07-14 | Q139 | 2022-05-30 | V67 | 2023-02-23 | V7 | B9 | fix action only
| J73 | 2020-01-30 | 13 | 8.075% | Q806 | 2020-06-17 | V11 | 2022-07-14 | T215 | 2022-07-14 | V136 | 2023-02-23 | V35 | BR62V | x
| J75 | 2020-01-30 | 14 | 8.696% | Q844 | 2020-06-17 | V175 | 2022-09-08 | T224 | 2022-07-14 | V159 | 2023-02-23 | V51 | BR64V | x
| J79 | 2020-01-30 | 15 | 9.317% | V2 | 2020-06-17 | V7 | 2022-09-08 | T258 | 2022-07-14 | V209 | 2023-02-23 | V97 |  | deleted
| J81 | 2020-01-30 | 16 | 9.938% | V3 | 2020-06-17 | V9 | 2022-09-08 | T323 | 2022-07-14 | V266 | 2023-02-23 | V157 |  | x
| J85 | 2020-01-30 | 17 | 10.56% | V14 | 2020-06-17 | V69 | 2027-04-15 | T404 | 2022-07-14 | V185 | 2023-02-23 | V267 |  | deleted
| J89 | 2020-01-30 | 18 | 11.18% | V29 | 2020-06-17 | V94 | 2027-04-15 | T406 | 2022-07-14 | V541 | 2023-02-23 | V295 |  | deleted
| J91 | 2020-01-30 | 19 | 11.8% | V106 | 2020-06-17 |  |  | T408 | 2022-07-14 | V168-FA | 2023-02-23 | V437 |  | x
| J121 | 2020-01-30 | 20 | 12.42% | V229 | 2020-06-17 |  |  | T410 | 2022-07-14 | V521-FA | 2023-02-23 | V441 |  | fix action only
| J151 | 2020-01-30 | 21 | 13.04% | V249 | 2020-06-17 |  |  | T412 | 2022-07-14 |  |  | V521 |  | deleted
| J165 | 2020-01-30 | 22 | 13.66% | V273 | 2020-06-17 |  |  | T414 | 2022-07-14 |  |  | V533
| J174 | 2020-01-30 | 23 | 14.29% | V471 | 2020-06-17 |  |  | T423 | 2022-07-14 |  |  | V537
| J207 | 2020-01-30 | 24 | 14.91% | V145 | 2020-06-17 |  |  | T425 | 2022-07-14 |  |  | V579
| J209 | 2020-01-30 | 25 | 15.53% | V196 | 2020-06-17 |  |  | T427 | 2022-07-14
| J210 | 2020-01-30 | 26 | 16.15% | V203 | 2020-06-17 |  |  | T429 | 2022-07-14
| J47 | 2020-01-30 | 27 | 16.77% | V282 | 2020-06-17 |  |  | J4 | 2022-07-14
| J103 | 2020-01-30 | 28 | 17.39% | V318 | 2020-06-17 |  |  | J45 | 2022-07-14
| J113 | 2020-01-30 | 29 | 18.01% | V322 | 2020-06-17 |  |  | J89 | 2022-07-14
| J119 | 2020-01-30 | 30 | 18.63% | V352 | 2020-06-17 |  |  | J230 | 2022-07-14
| J208 | 2020-01-30 | 31 | 19.25% | V428 | 2020-06-17 |  |  | J22 | 2022-09-08
| J614 | 2020-01-30 | 32 | 19.88% | V490 | 2020-06-17 |  |  | J46 | 2022-09-08
| J616 | 2020-01-30 | 33 | 20.5% | V542 | 2020-06-17 |  |  | J48 | 2022-09-08
| Q112 | 2020-01-30 | 34 | 21.12% | V39 | 2020-06-17 |  |  | J39 | 2022-09-08
| Q75 | 2020-05-21 | 35 | 21.74% | V93 | 2020-06-17 |  |  | J118 | 2022-09-08
| Q475 | 2020-05-21 | 36 | 22.36% | V139-FA | 2020-06-17 |  |  | J145 | 2022-09-08
| J14 | 2020-07-16 | 37 | 22.98% | V167-FA | 2020-06-17 |  |  | J186 | 2022-09-08
| J20 | 2020-07-16 | 38 | 23.6% | V268-FA | 2020-06-17 |  |  | J20 | 2022-09-08
| J41 | 2020-07-16 | 39 | 24.22% |  |  |  |  | J31 | 2022-09-08
| J43 | 2020-07-16 | 40 | 24.84% |  |  |  |  | J41 | 2022-09-08
| J45 | 2020-07-16 | 41 | 25.47% |  |  |  |  | J73 | 2022-09-08
| J52 | 2020-07-16 | 42 | 26.09% |  |  |  |  | J69 | 2022-09-08
| J73 | 2020-07-16 | 43 | 26.71% |  |  |  |  | Q63 | 2022-09-08
| J85 | 2020-07-16 | 44 | 27.33% |  |  |  |  | V154
| J89 | 2020-07-16 | 45 | 27.95% |  |  |  |  | V179
| J91 | 2020-07-16 | 46 | 28.57% |  |  |  |  | V243
| J40 | 2020-07-16 | 47 | 29.19% |  |  |  |  | V323
| J51 | 2020-07-16 | 48 | 29.81% |  |  |  |  | V362
| J53 | 2020-07-16 | 49 | 30.43% |  |  |  |  | V578
| J75 | 2020-07-16 | 50 | 31.06% |  |  |  |  | V5
| J81 | 2020-07-16 | 51 | 31.68% |  |  |  |  | V20
| J97 | 2020-07-16 | 52 | 32.3% |  |  |  |  | V35
| J210 | 2020-07-16 | 53 | 32.92% |  |  |  |  | V51
| J575 | 2020-07-16 | 54 | 33.54% |  |  |  |  | V56
| Q119 | 2020-09-10 | 55 | 34.16% |  |  |  |  | V66
| Q127 | 2020-09-10 | 56 | 34.78% |  |  |  |  | V70
| Q129 | 2020-09-10 | 57 | 35.4% |  |  |  |  | V97
| Q220 | 2020-09-10 | 58 | 36.02% |  |  |  |  | V155
| Q430 | 2020-09-10 | 59 | 36.65% |  |  |  |  | V267
| Q439 | 2020-09-10 | 60 | 37.27% |  |  |  |  | V454
| Q450 | 2020-09-10 | 61 | 37.89% |  |  |  |  | V311
| Q480 | 2020-09-10 | 62 | 38.51% |  |  |  |  | V325
| J109 | 2020-11-05 | 63 | 39.13% |  |  |  |  | V415
| J230 | 2020-11-05 | 64 | 39.75% |  |  |  |  | V417
| J62 | 2020-11-05 | 65 | 40.37% |  |  |  |  | V463
| J570 | 2020-11-05 | 66 | 40.99% |  |  |  |  | V18
| Q108 | 2020-11-05 | 67 | 41.61% |  |  |  |  | V115
| J2 | 2020-11-05 | 68 | 42.24% |  |  |  |  | V222
| J39 | 2020-11-05 | 69 | 42.86% |  |  |  |  | V241
| J61 | 2020-11-05 | 70 | 43.48% |  |  |  |  | V245
| J37 | 2020-11-05 | 71 | 44.1% |  |  |  |  | V321
| J55 | 2020-11-05 | 72 | 44.72% |  |  |  |  | V333
| J121 | 2020-11-05 | 73 | 45.34%
| Q419 | 2021-10-07 | 74 | 45.96%
| Q22 | 2021-10-07 | 75 | 46.58%
| Q54 | 2021-10-07 | 76 | 47.2%
| Q64 | 2021-10-07 | 77 | 47.83%
| Q437 | 2021-10-07 | 78 | 48.45%
| Q34 | 2021-10-07 | 79 | 49.07%
| Q29 | 2021-10-07 | 80 | 49.69%
| Y289 | 2021-10-07 | 81 | 50.31%
| Y299 | 2021-10-07 | 82 | 50.93%
| Y307 | 2021-10-07 | 83 | 51.55%
| Y438 | 2021-10-07 | 84 | 52.17%
| Y494 | 2021-10-07 | 85 | 52.8%
| AR3 | 2021-10-07 | 86 | 53.42%
| AR5 | 2021-10-07 | 87 | 54.04%
| AR7 | 2021-10-07 | 88 | 54.66%
| AR25 | 2021-10-07 | 89 | 55.28%
| Y291 | 2021-10-07 | 90 | 55.9%
| Y309 | 2021-10-07 | 91 | 56.52%
| Y323 | 2021-10-07 | 92 | 57.14%
| Y436 | 2021-10-07 | 93 | 57.76%
| AR12 | 2021-10-07 | 94 | 58.39%
| AR15 | 2021-10-07 | 95 | 59.01%
| AR16 | 2021-10-07 | 96 | 59.63%
| AR17 | 2021-10-07 | 97 | 60.25%
| AR18 | 2021-10-07 | 98 | 60.87%
| AR21 | 2021-10-07 | 99 | 61.49%
| AR23 | 2021-10-07 | 100 | 62.11%
| J150 | 2021-12-02 | 101 | 62.73%
| J193 | 2021-12-02 | 102 | 63.35%
| J222 | 2021-12-02 | 103 | 63.98%
| J225 | 2021-12-02 | 104 | 64.6%
| J42 | 2021-12-02 | 105 | 65.22%
| J191 | 2021-12-02 | 106 | 65.84%
| Q101 | 2022-09-08 | 107 | 66.46%
| Q107 | 2022-09-08 | 108 | 67.08%
| Q111 | 2022-09-08 | 109 | 67.7%
| Q117 | 2022-09-08 | 110 | 68.32%
| Q131 | 2022-09-08 | 111 | 68.94%
| Q133 | 2022-09-08 | 112 | 69.57%
| Q167 | 2022-09-08 | 113 | 70.19%
| Q445 | 2022-09-08 | 114 | 70.81%
| Q481 | 2022-09-08 | 115 | 71.43%
| Q22 | 2022-09-08 | 116 | 72.05%
| Q60 | 2022-09-08 | 117 | 72.67%
| Q85 | 2022-09-08 | 118 | 73.29%
| Q87 | 2022-09-08 | 119 | 73.91%
| Q97 | 2022-09-08 | 120 | 74.53%
| Q99 | 2022-09-08 | 121 | 75.16%
| Q109 | 2022-09-08 | 122 | 75.78%
| Q113 | 2022-09-08 | 123 | 76.4%
| Q135 | 2022-09-08 | 124 | 77.02%
| Q409 | 2022-09-08 | 125 | 77.64%
| Q34 | 2022-09-08 | 126 | 78.26%
| Q419 | 2022-09-08 | 127 | 78.88%
| Q75 | 2022-09-08 | 128 | 79.5%
| Y291 | 2022-09-08 | 129 | 80.12%
| Y309 | 2022-09-08 | 130 | 80.75%
| Y319 | 2022-09-08 | 131 | 81.37%
| Y323 | 2022-09-08 | 132 | 81.99%
| J37 | 2022-11-03 | 133 | 82.61%
| J55 | 2022-11-03 | 134 | 83.23%
| J79 | 2022-11-03 | 135 | 83.85%
| J121 | 2022-11-03 | 136 | 84.47%
| J165 | 2022-11-03 | 137 | 85.09%
| J174 | 2022-11-03 | 138 | 85.71%
| J191 | 2022-11-03 | 139 | 86.34%
| J207 | 2022-11-03 | 140 | 86.96%
| J209 | 2022-11-03 | 141 | 87.58%
| J506 | 2022-11-03 | 142 | 88.2%
| J561 | 2022-11-03 | 143 | 88.82%
| J563 | 2022-11-03 | 144 | 89.44%
| J573 | 2022-11-03 | 145 | 90.06%
| J582 | 2022-11-03 | 146 | 90.68%
| J585 | 2022-11-03 | 147 | 91.3%
| J14 | 2022-11-03 | 148 | 91.93%
| J24 | 2022-11-03 | 149 | 92.55%
| J52 | 2022-11-03 | 150 | 93.17%
| J68 | 2022-11-03 | 151 | 93.79%
| AR15 | 2022-11-03 | 152 | 94.41%
| AR16 | 2022-11-03 | 153 | 95.03%
| AR17 | 2022-11-03 | 154 | 95.65%
| AR18 | 2022-11-03 | 155 | 96.27%
| AR19 | 2022-11-03 | 156 | 96.89%
| AR21 | 2022-11-03 | 157 | 97.52%
| AR22 | 2022-11-03 | 158 | 98.14%
| AR23 | 2022-11-03 | 159 | 98.76%
| AR24 | 2022-11-03 | 160 | 99.38%
| Q947 | 2022-11-03 | 161 | 100%
UPDATE

## DashBoard
| J | Q | AR | Y | TOTAL
Total | 85 | 40 | 20 | 14 | 159
# Completed as of 10/7/2021 | 60 | 19 | 11 | 10 | 100
% Completed as of 10/7/2021 | 70.59% | 47.5% | 55% | 71.43% | 62.89%
# Remaining | 25 | 21 | 9 | 4 | 59